## requirements
Requiements attached
# | Tasks | Time | Perference | Sprint No.
1 | As an admin, I want to edit information's org | 0.5 | Highest | 1
2 | As an admin, I want to edit identity of the org's site | 0.5 | Highest | 1 | sprint_1 | 17
3 | As an admin, I want to enter partners data | 1.5 | Meduim | 1 | sprint_2 | 5
4 | As an admin, I want to enter donors data | 0.5 | Medium | 1 | sprint_3 | 7
5 | As an admin, I want to enter supportives data | 0.5 | Medium | 1
6 | As an admin, I want to upload a report file | 1.5 | High | 1
7 | As an admin, I want to add a project to be carried out that contains activites | 3 | Highest | 1
8 | As a visitor, I want to browse projects | 1 | Highest | 1
9 | As a visitor, I want to see site information | 0.5 | High | 1
10 | As a visitor, I want to browse project's activties | 1 | Highest | 1
11 | As a follower, I want to apply for the volunteering form(ثم إرسال إيميلات بالموافقة أو الرفض) | 1.5 | Hight | 1
12 | As a visitor, I want to contact with site | 0.5 | Low | 1
13 | As an admin , I want to view visitors message | 0.5 | Low | 1
14 | As a visitor, I want to see reports of different types | 2 | High | 1
15 | As an admin, I want to advertise for something | 0.5 | Lowest | 1
16 | As a site visitor, I want to see the latest advertisment | 1.5 | Lowest | 1
17 | As an admin, I want to post an event | 1 | Low | 2
18 | As a visitor , I want to browse events | 1.5 | Low | 2
19 | As a visitor , I want to add comment on any project | 1 | Low | 2
20 | As an admin , I want to view and approve/reject the visitors comments | 1.5 | Low | 2
21 | As an admin I want to test the control panel | 2 |  | 3
22 | As an admin I want to twst the web site | 2 |  | 3
23 | As admin I want to deploy the project | 3 |  | 3

## sprints
Sprints attached
# | Epics | Sprint | Time
| Profile ,Project ,Participation,Report | Sprint 1 | 17 days
| Activity ,Ads | Sprint 2 | 5 days
| Test | Sprint 3 | 1 Week